**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

Lead Agency (FHWA or State DOT): \_\_\_**FHWA**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |
| --- | --- |
| **Transportation Pooled Fund Program Project #**TPF-5(454) | **Transportation Pooled Fund Program - Report Period:**□ Quarter 1 (January 1 – March 31) □ Quarter 2 (April 1 – June 30)X Quarter 3 (July 1 – September 30)□ Quarter 4 (October 1 – December 31) |
| **Project Title:**Update Precipitation Frequency Estimates for the Northwest (NOAA Atlas 14, Vol. 12) |
| **Name of Project Manager(s):**Megan Frye | **Phone Number:**(303) 396-9847 | **E-Mail**megan.frye@dot.gov |
| **Lead Agency Project ID:**FHWA | **Other Project ID (i.e., contract #):** | **Project Start Date:**June 3, 2020 |
| **Original Project End Date:**December 2023 | **Current Project** End Date:December 2023 | **Number of Extensions:** |

Project schedule status:

X On schedule □ On revised schedule □ Ahead of schedule □ Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Budget** | **Total Cost to Date for Project** |  **Percentage of Work**  **Completed to Date** |
| $640,894 | $439,104 | 50% |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
|  **Total Project Expenses**  **and Percentage This Quarter** |  **Total Amount of Funds**  **Expended This Quarter** |  **Total Percentage of**  **Time Used to Date** |
| $182,704 / 50% | $182,704 | 40% |

|  |
| --- |
| **Project Description**:The purpose of this study is to determine precipitation frequency estimates for Idaho, Montana and other the Northwest States for durations of 5-minute through 60-day at average recurrence intervals (ARIs) of 1-year through 1,000-year. The estimates and associated bounds of 90% confidence intervals will be provided at 30 arc-sec resolution (approximately 800 x 800 m; varies with latitude). The study results will be published as volumes of NOAA Atlas 14, a wholly web-based publication available at www.nws.noaa.gov/ohd/hdsc. The publication will include the artifacts provided in previous NOAA Atlas 14 Volumes, including access through the Precipitation Frequency Data Server, base grids in standard formats together with error estimates, electronic copies of maps, charts of seasonal distributions and probabilistic temporal distributions of heavy precipitation, and detailed documentation. Updated areal reduction factors, which are needed to calculate analogous areal precipitation frequency estimates, will be developed as a separate appendix to NOAA Atlas 14 for the entire U.S. They include regional frequency analysis based on L-moments including error estimates, a combination of PRISM based techniques and CRAB for spatial interpolation, techniques for the analysis of climatic trend, temporal distribution and seasonality, internal consistency checks and variety of automated processes designed to enhance productivity. Intermediate results in the form of hourly and daily estimates at several ARIs will be distributed for peer review as will the final documentation. |

|  |
| --- |
| **Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):**During July to September 2022 reporting period, NOAA completed quality control for daily stations at base duration and began working on mean annual maximum and conversion factors. In this reporting period, NOAA completed the daily AMS quality control task (Task 1) and implemented a total of 2,523 corrections to the daily annual maximum time series data in this project area. In addition, they implemented 12,948 corrections to the GHCN NCEI dataset involving conflicts between the PRCP (1-day) and MDPR (multiday) precipitation variables.Additional information is on the status of the Atlas 14, Volume 12 work is available at: https://www.weather.gov/owp/hdsc\_current\_projects |
| **Anticipated work next quarter**:The large portion of the work in the next reporting period will be on finalizing quality control of AMS data for base durations (1-hr, 12-hr, 10-days). NOAA will complete conversion factors and the rainy season, and plan to review mean annual maximum grids at base duration. The project milestone schedule has been revised to align with the availability of funds and personnel. Current Project Schedule* Data collection, formatting, and initial quality control
	+ Complete
* Extraction of annual maximum series (AMS); additional quality control and data reliability tests
	+ In progress; January 2023
* Regionalization and frequency analysis
	+ March 2023
* Initial spatial interpolation of precipitation frequency (PF) estimates and consistency checks across durations
	+ March 202
* Peer review
	+ June 2023
* Revision of PF estimates
	+ November 2023
* Remaining tasks (e.g., development of precipitation frequency estimates for partial duration series, seasonality, temporal distributions, documentation)
	+ December 2023
* Web publication
	+ December 2023
 |

|  |
| --- |
| **Significant Results:**Work completed thus far will result in a database of observations and extracted AMS data for durations from 15- min to 60-day, as available. Those data will be used in subsequent analyses. Observations found lacking in quality in subsequent analyses will be excluded from the database for that time, and any time series such data contributes to will be re-extracted. Non-NCEI data digitized as part of this activity will be shared with the NCEI for inclusion in the NOAA archive for broader public access. |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that** **might affect the completion of the project within the time, scope and fiscal constraints set forth in the** **agreement, along with recommended solutions to those problems).**Delay in finalizing the IAA with NOAA. Estimated timeline to complete the work still on track for Q4 of 2023. |

|  |
| --- |
| **Potential Implementation:** All deliverables will be accessible through the Precipitation Frequency Data Server (PFDS). That includes:* Interactive map of the United States. Via this map, IDF/DDF tables and curves will be available for any location in the project area.
* Precipitation frequency grids in GIS compatible formats.
* Metadata in Federal Geographic Data Transfer Standard format.
* Cartographic maps of precipitation frequency estimates.
* Charts of the seasonal distribution of annual maxima
* Probabilistic temporal distributions for 6-hour, 12-hour, 24-hour, and 96-hour durations in both chart and digital form
* Rainfall frequency estimates with corresponding upper and lower bounds of 90% confidence intervals will be available at 30-arc sec grid for durations of 1, 2, 3, 6, 12 and 24 hours.
 |