**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

Date: \_\_9/30/2013\_\_\_\_\_\_\_\_\_

Lead Agency (FHWA or State DOT): \_\_FHWA\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |
| --- | --- |
| **Transportation Pooled Fund Program Project #***(i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX)*SPR-3 (089) | **Transportation Pooled Fund Program - Report Period:**□Quarter 1 (January 1 – March 31)□Quarter 2 (April 1 – June 30)🗹Quarter 3 (July 1 – September 30)□Quarter 4 (October 1 – December 31) |
| **Project Title:** |
| **Name of Project Manager(s):**Eloise F. Powell | **Phone Number:**860-494-7566 | **E-Mail**Eloise.powell@dot.gov |
| **Lead Agency Project ID:**DTFH61-10-H-00007  | **Other Project ID (i.e., contract #):**NETC 05-5 | **Project Start Date:**04/22/2010 (w/FHWA) |
| **Original Project End Date:**CTDOT contracts expired, with FHWA-CTtaking over w/FHWA HQ to completeprojects. | **Current Project End Date:**NETC 05-5: 9/23/2013 | **Number of Extensions:** 0 |

Project schedule status:

□ On schedule □ On revised schedule □ Ahead of schedule 🗹 Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
|  **Total Project Budget** |  **Total Cost to Date for Project** |  **Percentage of Work**  **Completed to Date** |
| 05-5: $20,012.00  | 05-5: $19,907.99 |  96% |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
|  **Total Project Expenses**  **and Percentage This Quarter** |  **Total Amount of Funds**  **Expended This Quarter** |  **Total Percentage of**  **Time Used to Date** |
| NETC 05-5:0 |  0 |  100% |

|  |
| --- |
| **Project Description**:**05-5** **(FHWA):**: Measurement of Adhesion Properties Between Topcoat Paint and Metallized/Galvanized Steel with Surface Energy Measurement EquipmentPI: Sze Yang, University of Rhode Island |

|  |
| --- |
| **Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):****05-5** **(FHWA):** Measurement of Adhesion Properties Between Topcoat Paint and Metallized/Galvanized Steel with Surface Energy Measurement Equipment* Final Report was reviewed by Technical Committee and the NETC Coordinator.
 |
| **Anticipated work next quarter**:**05-5** **(FHWA):** Final Report editing in preparation for printing Final Report for distribution; and then FHWA CT can recommend the final invoice for payment to the FHWA HQ CO, and close project out. |

|  |
| --- |
| **Significant Results:**NETC 05-5 is very close to being completed**.**  |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that** **might affect the completion of the project within the time, scope and fiscal constraints set forth in the** **agreement, along with recommended solutions to those problems).**The PI is taking an exorbitant amount of time to complete the draft and final reports for review and publication.  |

|  |
| --- |
| **Potential Implementation:** Additional webinars to broadcast research results and products by the TMC pooled fund study will be arranged and rolled out on a quarterly basis. |