|  | OREGON DEPARTMENT OF TRANSPORTATION SPR Quarterly Progress Report 9/1/20 through 12/31/20 | Research Section Mill Creek Building 555 13th Street, Salem, OR 97301 ph: 503-986-2700 fax: 503-986-2844 |
| --- | --- | --- |

Date:	Friday, January 22, 2021

TO:	Technical Advisory Committee (TAC) Members:

Albert Nako, Oregon Sr Standards Engineer, 			ph: (503) 986-3333

Email albert.nako@odot.state.or.us

Jon Lazarus (Chair), Lead Agency Contact (Oregon),	 	ph: (503) 986-2852

Email jon.m.lazarus@odot.state.or.us

Bijan Khaleghi, Washington State Bridge Design Engineer, 	ph (360) 705-7181

Email	KhalegB@wsdot.wa.gov

Michael Knapp, Alaska Statewide Hydraulics Engineer, 	ph: (907) 465-8893

Email: michael.knapp@alaska.gov

Dean Takiguchi, Hawaii State Bridge Engineer			ph (808) 692-7614

Email: Dean.Takiguchi@hawaii.gov

James Fu, Incoming Hawaii State Bridge Engineer		ph (808) 692-7611

Email: james.fu@hawaii.gov

Tom Shantz, California State Bridge Engineer,			ph: (916) 207-8841

Email: tom.shantz@dot.ca.gov

Sheila Duwadi, FHWA,	 					ph (202) 493-3106

Email sheila.duwadi@dot.gov
	Mr Michio Osumi, PWRI (Japan)					ph ()

Email: m-oosumi@pwri.go.jp

FRIENDS OF THE TAC:

Kornel Kerenyi, FHWA Turner Fairbanks		Kornel.Kerenyi@dot.gov

Rich Pratt, Alaska					richard.pratt@alaska.gov

Elmer Marx, Alaska					elmer.marx@alaska.gov

Tom Ostrom, Caltrans				tom.ostrom@dot.ca.gov

Kevin Baskin, BC					Kevin.Baskin@gov.bc.ca

Solomon Yim, OSU					yims@ENGR.ORST.EDU

Michael Scott, OSU					michael.scott@oregonstate.edu

Ian Buckle, UNR					igbuckle@unr.edu

Marc Eberhard, UW					eberhard@u.washington.edu

Michael Motley, UW					mrmotley@uw.edu

Mark Yashinski, Caltrans, 				mark.yashinsky@dot.ca.gov

FROM:	Patrick Lynett, PEER Project Manager, Professor Coastal Engineering @ USC

Ph (213) 740-3133				Email: plynett@usc.edu

And

Amarnath Kasalanati, Executive Director, PEER, University of California Berkley

Ph (510) 642-6475				Email: amarnath1@berkeley.edu

1. 	Project

Validation of Tsunami Design Guidelines for Coastal Bridges

SPR 	TPF 5(307)

Project Description

The functionality and survivability of coastal bridges under earthquake and tsunami excitations is a major concern of western US states.  A significant number of these bridges are vital to the emergency first response transportation of coastal cities immediately after a Cascadia Subduction Zone earthquake or other major earthquake events that generate tsunami waves in the Pacific Ocean, which will likely be followed by a local tsunami 15 to 60 minutes afterward.  At least two numerical studies sponsored by California and Oregon of tsunami loads on a number of coastal bridges have been completed or nearly completed. Several studies have also been conducted on the effects of the “Great Japan Earthquake” of 2011 by Japanese research institutes as well as at UNR.  Significant progress in the development of a tsunami design guideline has been made and the results appear promising. However, the reliability of the numerical results is unknown at this point due to a lack of experimental data needed for verification and validation.  Thus, it is essential that experiments be conducted to provide data to verify and validate the numerical results to assess the accuracy of the load prediction equations.  When validated, the numerical model can then be used to further improve the numerical analysis and development of practice design guidelines.

2.	Key Dates

Start Date for ODOT:			April 16, 2015 (contract execution)

Completion Date for ODOT:			June 30, 2018 (Amended to June 30, 2020)

3.	Principal Investigator and Teams

Patrick Lynett, Project Manager	plynett@usc.edu			213-740-3133

Amarnath Kasalanti, PEER		amarnath1@berkeley.edu		510-642-6475

Jon Lazarus, Lead Agency Contact	jon.m.lazarus@odot.state.or.us 	503-986-2852

Hong Kie Thio, 			hong.kie.thio@aecom.com		213-996-2250

Michael Scott				michael.scott@oregonstate.edu	541-737-6996

Tom Murphy				TPMurphy@modjeski.com		717-790-9565 x425

Tom Shantz				tom.shantz@dot.ca.gov		916-227-7245

Relationship/Project Chart

Original Planned Project Schedule

4.	Progress

| Working Group 1: Tsunami Hazard and Mapping | 30% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 95% |
| Percent completed after this quarter: | 100% |

Key Progress-To-Date

Problems

- See Project Summary

| Working Group 2: Tsunami Loading of Bridges | 30% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 75%1 |
| Percent completed after this quarter: | 100% |

Key Progress-To-Date

Problems

See Project Summary

| Working Group 3: Bridge Detailing for Tsunami Loads | 3% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 10%1 |
| Percent completed after this quarter: | 100% |

Key Progress-To-Date

Problems

See Project Summary

| Working Group 4: Geotechnical Issues (Scour and drawdown induced liquefaction) | 4% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 10%1 |
| Percent completed after this quarter: | 100% |

Key Progress-To-Date

Problems

N/A

| Working Group 5: Guide Specifications for Bridge Design for Tsunami Hazard | 33% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 15%1 |
| Percent completed after this quarter: | 15% |

Key Progress-To-Date

Problems

See Project Summary

| CONTINGENCY PLAN FOR DEVELOPING 1000-YR HAZARD MAPS | 0% |
| --- | --- |
| Percent completed reported in last quarterly report: | 95%1 |
| Percent completed after this quarter: | 100% |

Key Progress-To-Date

Problems

- N/A

7.	Finances

SPR Project Summary

Total PEER contract = $435,000.00                               Total UNR contract = $85,632.00  Total cost of contracts = $520,632.00               Total commitments received = $622,100.00

8.	Project Summary (Completed by ODOT)

This quarterly report will summarize the events between March 20181 and December 2020.

There were concerns raised with the mapping for Working Group 1 and reporting was not submitted timely. The calculations were reviewed externally and the group asked for re-calculations and to complete the paper explaining the methodology. These were produced, but with a significant delay. The work to reproduce the calculations and report were completed in 2019.

During the normal course of the project development, the TAC believed in hiring a 3rd party to use numeric modeling to verify bridge loading scenarios from Working Group 2. The group hired the University of Reno Nevada (UNR) to conduct this additional work. This caused an extended delay in the project and additional funds were requestsed to add to the Pool Fund. The TAC believed the quality of research and cross-comparison between Working Group 2 and UNR’s work was beneficial to the study. UNR’s work will be published seperately under the same ODOT Publications link and recognized within the final report. The research UNR completed (compare loading) delayed the publication of the final PEER report, which was an accepted delay by the TAC. Additionally, UNR was affected by the coronavirus outbreak in 2020, which further delayed the project from producing a draft final report.

The Oregon Bridge Engineer, Bruce Johnson, retired in 2019. Bruce’s knowledge, support, and drive to complete the project was very much missed. ODOT found a his permanent replacement after a long search, but this too delayed the project from completion.

The project was completed in June 2020 with the submission of the PEER final report. A goal of the project was to have a submission-ready publication for AASHTO sub-committee review and balloting. Although, the timeframe for balloting was outside of the project timeframe, this was submitted in November 2020. The ODOT report publication link is: https://www.oregon.gov/odot/Programs/Pages/Research-Publications.aspx

Specifically, The Tsunami Guidelines PEER report link is here: https://www.oregon.gov/odot/Programs/ResearchDocuments/TsunamiFinal.pdf

Jon Lazarus

# Footnotes

Last quarterly report was March 2018

This value includes the Oregon contingency work and is identified as a “not to exceed” amount in Amendment 1 (signed 11/30/2017).

TPF website http://www.pooledfund.org/Details/Study/556

# Text boxes

Technical Advisory Committee,

Chair Bruce Johnson, rep Jon Lazarus

Patrick Lynett, PM and

Amarnath Kasalanti

Working Group 1, Tsunami Hazard and Mapping, Lead

Hong Kie Thio

Working Group 2, Tsunami Loading of Bridges, Lead Michael Scott

Working Group 3, Bridge Detailing for Tsunami Loads, Lead Tom Murphy

Working Group 4, Geotechnical Issues,

Lead

Tom Shantz

Working Group 5, Guide Specifications for Bridge Design, Lead Tom Murphy