TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency:  Minnesota DOT

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # TPF-5(192) | Transportation Pooled Fund Program - Report Period: □Quarter 1 (January 1 – March 31) □Quarter 2 (April 1 – June 30) x Quarter 3 (July 1 – September 30) □Quarter 4 (October 1 – December 31) |
| --- | --- |
| Project Title: Loop and Length Based Vehicle Classification |
| Name of Project Manager(s): Gene Hicks, Mn/DOT | Phone Number: 651/366-3856 | E-Mail Gene.Hicks@state.mn.us |
| Lead Agency Project ID: #95029 | Other Project ID (i.e., contract #): | Project Start Date: 1/29/2010 |
| Original Project End Date: 5/31/2012 | Current Project End Date: 5/31/2012 | Number of Extensions: 0 |

Project schedule status:

□ On schedule	□ On revised schedule		□ Ahead of schedule		x Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $485,000 | $241,279 (consultant expenses) $4,538 (kickoff meeting expenses) $10,600 (2010 NATMEC expenses) Total: $256,417 | 53 percent |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| $53,085 (consultant expenses) 11 percent | $53,085 (consultant expenses) | 75 percent |

Project Description: Field test installation methods for loops to determine the most cost effective and best performing procedures and materials. Determine the number of bins and the length spacing for each of those bins for uniform collection of length based classification data. Establish calibration standards for vehicle length based measurements.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): Ten loops were installed at the new I-35 test site near Wyoming, MN. Non-loop sensors were installed and tested at the I-394 NIT Test Site. The Test Plan was revised to reflect the new primary loop testing site. The following sensors were tested: Wavetronix HD, Canoga Microloops, Hi-Star. The Project Team coordinated with LTPP and Michigan DOT for multi-state data gathering as a preliminary step to conducting Task 6, Determine Feasibility of LBVC Bins.

Anticipated work next quarter: Conduct loop-based testing at I-35 Test Site. If Sensys detectors are ready, conduct Sensys testing at Mn/ROAD. Analyze data. Establish draft loop detector accuracy standards. Complete analysis of feasibility of LBVC bins.

Significant Results: Testing phase is currently underway. Preliminary laboratory findings are available.

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems). Delays in contracting and starting the project pushed the initial schedule back two months. Also, the loops installed at the Mn/ROAD Test Site were found to be unsuitable for this research, so alternative methods for testing the loops are under consideration. Loops were installed at the I-35 Test Site which incurred additional expense for installation and coordination. A proposed amendment is expected to address this concern. The project will remain on schedule if testing is conducted in fall 2011 with data analysis immediately following in the winter 2011-2012. Note: consultant contract has been split into two phases. Phase 1 consists of tasks 1 through 4, and phase 2 consists of tasks 5 through 8. Work on both phases is currently underway.

Potential Implementation: This project will recommend a loop detector calibration process and accuracy standards. This project will develop length-based vehicle classification schemes.