**HSM Implementation Pooled Fund Study**

**TPF-5(255)**

**Quarterly Report**

**April - June 2014**

**Participating Agencies:** CA, ID, IL, LA, NC, KS, OH, OK, OR, MS, PA, MO, NV, WA, WV, and WI

**Total Funds Committed:** $1.135,000

**Total Funds Transferred to FHWA:** $730,078

**Total Fund Spent:** $236,500

**Activities accomplished during Reporting Period (April 1 – June 30, 2014):**

* Conducted conference call with pooled-fund State representatives to discuss Survey of HSM Implementation on April 24, 2014
* Conducted conference call with pooled-fund State representatives to discuss SPF calibration and development efforts on April 30, 2014
* Drafted statement of work for project on “Scale and Scope of HSM Implementation in the Project Development Process,” obtained review comments from several pooled-fund State representatives, finalized statement of work, and submitted it to the FHWA procurement process. The estimated budget is $250,000.
* Completed literature search of State’s SPF development and/or calibration efforts, identified 10 States with published results, and drafted a summary of those results.
* Obtained support from NCHRP 17-50 Panel Chair and NCHRP staff person to include pooled-fund State representatives who are not lead States among the participants in future HSM Lead State Peer Exchanges. TPF-5(255) would pay for the representatives from pooled-fund States that are not also lead States.

**Activities planned for next quarter (July 1 – September 30, 2014)**:

* Distribute summary of States SPF development and calibration efforts for review by pooled-fund State representatives. Finalize summary and post it at the pooled-fund Study web site.
* Conduct evaluation of proposals and award contract for project entitled “Scale and Scope of HSM Implementation in the Project Development Process.” April Renard from Louisiana DOTD will represent the pooled-fund States on the evaluation panel.
* Submit Work Order Proposal Request under FHWA cooperative agreement with AASHTO to conduct survey of HSM implementation and resource needs assessment.
* Conduct a conference call with pooled-fund State representatives to discuss status of priority projects and to identify additional priority projects.