Click here to enter Program or Project Title

Progress Report – Click here to enter a date.

Title: Assessment and Repair of Prestressed Bridge Girders Subjected to Over-height Truck Impacts Pooled Fund Project

Project Number: TR202011

Principal Investigator (PI): Mohamed ElGawady PhD (PI)

Co-PI(s): William Schonberg PhD, PE (Co-PI)

| Award date: | 1/1/2021 |  |  |
| --- | --- | --- | --- |
| Scheduled completion date: | 12/31/2023 | % of project completed to date: | 81% |
| Total budget: | $805,000 | % of budget expended to date: | 72% |
| Draft report due: | 9/30/2023 | Final report due: | 12/1/2023 |  |

Provide a short description of the work currently underway.

Use additional notes section if you need to provide more information.

Task 2. Experimental testing of bridge girders subjected to lateral impacts:

- 2nd girder is being prepared for testing and will be ready for testing in two weeks after modifying the test setup to revise the boundary conditions.

- A second set of beams (five girders) is placed at Core slab (see pictures 1 through )

Provide a short description of the noteworthy activities/accomplishments during this reporting period.

Use additional notes section if you need to provide more information.

Task 5: Repair Evaluation:

- Preparing the flexural testing of the 1st repaired beam. Fig. 2 through 5 show the repaired beam and main results.

| (a) |  |
| --- | --- |
| (b) |  |
| (c) Fig. 1: Placing strain gauges on steel cages for the second set of girders. |  |

| Fig. 2: Repaired beam 1 ready for testing (a) Front view of repaired girder, and (b) Rear view of the repaired girder with flexural test setup |  |
| --- | --- |

Fig. 3: Measuring the beam deflection at mid-span using LVDT

| (a) | (b) |
| --- | --- |
| (c) |  |
| Fig. 4: Damage of the strengthened beam (a) Flexure-shear crack at 70 kips, (b) Debonding of Transverse CFRP, and (c) Rear view of damaged beam |  |

| (a) | (b) |
| --- | --- |
| Fig. 5: Test results (a) Load - deflection curve at midspan of girder, and (b) Longitudinal FRP strains |  |