**QUARTERLY PROGRESS REPORT**

**April through June 2023**

**DELIVERING TECHNICAL ASSISTANCE TO FEDERAL, STATE, AND LOCAL HIGHWAY AGENCIES FOR EFFECTIVE ADOPTION OF BIG DATA AND BIG DATA ANALYTICS BASED HIGHWAY TRAFFIC PARAMETERS**

FHWA Pooled Fund Study # TPF-5(384)

Submitted by:

FHWA

**WORK CONDUCTED THIS QUARTER**

* Meeting with the MT DOT, delay getting the data until the end of June
* Agenda set for TAC meetings
* Updated guidance document received by FHWA
* Updated guidance document reviewed by FHWA
* Revisions completed Battelle on updated guidance document
* Travel plans announced to TAC members and federal staff

**WORK PLANNED FOR NEXT QUARTER**

* Work on next phase of PF
	+ Updates for task 3 report
	+ Technical assistance for agencies – MT and others as received
	+ TAC Technical Exchange Sessions – Denver and Columbus

**SIGNIFICANT ISSUES**

* None