| State Planning and Research Program Quarterly Report |
| --- |
| PROJECT TITLE: Clear Roads Administration, Research Support and Information Services OBJECTIVES: Clear Roads is a pooled fund research project aimed at rigorous testing of winter maintenance materials, equipment and methods for use by highway maintenance crews. The Clear Roads Technical Advisory Committee contracted with CTC & Associates LLC to perform the administrative functions associated with maintaining the pooled fund project as well as information services that support technology transfer. This report summarizes activities conducted under this contract over the last three months. |
| PERIOD COVERED: July through September 2014 |
| PARTICIPATING AGENCIES: Minnesota Department of Transportation |
| PROJECT MANAGER: Tom Peters LEAD AGENCY: MnDOT PRINCIPAL INVESTIGATOR: CTC & Associates LLC | SP&R PROJECT NO: Contract #02337 | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $224,900 | PROJECT EXPENDITURES TO DATE: $171,966.46 |
| WORK COMPLETED: TAC Meetings Coordinated a face-to-face meeting of the Clear Roads Technical Advisory Committee on September 9-10, 2014 in Kansas City, MO. Began planning for a face-to-face meeting of the Clear Roads Technical Advisory Committee on March 17-19, 2014 in Cour d’Alene, Idaho. Planning includes all preparations for the meeting such as communication with TAC members, meeting logistics, agenda and meeting materials. Drafted meeting minutes and followed up on action items from the Fall 2014 meeting. Supported planning for the 2015 Winter Maintenance Peer Exchange. Administration and Marketing Updated the Clear Roads website with current TAC members, project status and meeting information. Maintained and updated commitment, obligation, and overall budget information for the pooled fund in coordination with MnDOT. Supported efforts of TAC members in recruiting new members and talking about Clear Roads at conferences. Information Services Researched, wrote and published the August winter maintenance news. Distributed Clear Roads updates (final reports, RFPs, newsletters, etc.) to the Clear Roads distribution list using Constant Contact. Finalized and posted the results of the 2013-14 product experience survey on the Clear Roads website. Redesigned and launched the Clear Roads website to provide a fresh look using a content management system. Research Support New projects Worked with the subcommittees to develop the scopes of work and post formal RFPs for the following research projects selected by the TAC for funding in March 2014: Synthesis on GPS/AVL Equipment Used for Winter Maintenance Quantifying the Impact that New Capital Projects Will Have on Roadway Snow and Ice Control (RSIC) Operations Developing a Training Video and Manual for Best Practices and Techniques in Clearing Different Interchange Configurations and Other Geometric Layouts Plug and Play Phase II Snow Removal Performance Metrics – Phase I: Synthesis Use Of Equipment Lighting During Snowplow Operations Snowplow Route Optimization Winter Severity Mapping Enhancement Development of a Winter Driver's Education Program Roadway Salt Best Management Practices Worked with the subcommittee to develop the scope of work and formal RFP for the Plug and Play Test Bed Software project funded in 2013. Coordinated communication between the subcommittee and NHTSA on the Winter Driver Education project. Research in progress Continued Coordination with the PI and subcommittee to schedule check-in teleconferences and facilitate the review of interim and final deliverables for: Establishing Effective Salt and Anti-icing Application Rates Understanding the Chemical and Mechanical Performance of Snow and Ice Control Agents on Porous or Permeable Pavements Comparison of Materials Distribution Systems Best Practices for the Prevention of Corrosion to DOT Equipment: A User’s Manual Developing Test Bed Software to Qualify Plug and Play Technology Snow and Ice Control Environmental Best Management Practices Manual Understanding the Effectiveness of Non-Chlorine Liquid Agricultural By-Products and Solid Complex Chloride/Mineral Products Used in Snow and Ice Control Operations Plug and Play Initiative: Coordinated with the project subcommittees and other stakeholders and promoted the second public comment period for the protocol. This included developing a public comment form and tracking versions of the protocol. Completed research Coordinated with the Implementation and Technology Transfer subcommittee to develop recommendations for implementation and technology transfer for completed Clear Roads research projects. |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: Research, write and publish the November Winter Maintenance E-News. Develop the 2014-2015 Product Experience Survey. Continue planning for a face-to-face meeting of the Clear Roads Technical Advisory Committee on March 17-19, 2014 in Cour d’Alene, Idaho: travel logistics, agenda, etc. Continue to coordinate and support the RFP development, evaluation and contracting processes for the 2014 funded projects: Development of a Winter Driver's Education Program (RFP Development) Plug and Play Phase II (evaluation) Snow Removal Performance Metrics – Phase I: Synthesis (evaluation) Developing a Training Video and Manual for Best Practices and Techniques in Clearing Different Interchange Configurations and Other Geometric Layouts (contracting) Roadway Salt Best Management Practices (contracting) Snowplow Route Optimization (contracting) Use Of Equipment Lighting During Snowplow Operations (contracting) Winter Severity Mapping Enhancement (contracting) Synthesis on GPS/AVL Equipment Used for Winter Maintenance (contracting) Quantifying the Impact that New Capital Projects Will Have on Roadway Snow and Ice Control (RSIC) Operations (contracting) Continue to coordinate with investigators and the Clear Roads subcommittees on projects in progress. Distribute interim and final deliverables. Coordinate final webinar presentations for projects that are completing. Write two-page briefs for the completing projects. Maintain the Clear Roads website and budget. Provide support for the review and processing of investigator invoices, as needed. Begin planning for the Fall 2015 Clear Roads TAC meeting (conference facilities, travel arrangements, vendor selection, etc.). |
| STATUS AND COMPLETION DATE: The funds expended are a little ahead of schedule. This is due in part to the intense focus on temporary or cyclical activities, such as the new website, the fall meeting, and multiple article submissions. However, the TAC also selected a record number of projects for funding at the spring meeting, which has required more RFP development and contracting support than anticipated. CTC expects to expend fewer hours in the next quarter as our focus turns primarily to research project support and planning for the spring meeting. The contract is scheduled to end August 31, 2015. |