**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

Lead Agency (FHWA or State DOT): \_\_\_FHWA\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |
| --- | --- |
| **Transportation Pooled Fund Program Project #***TPF-5(454)* | **Transportation Pooled Fund Program - Report Period:**□Quarter 1 (January 1 – March 31)□Quarter 2 (April 1 – June 30)XQuarter 3 (July 1 – September 30)□Quarter 4 (October 1 – December 31) |
| **Project Title:**Updating U.S. Precipitation Frequency Estimates for the Northwest |
| **Name of Project Manager(s):**Cynthia Nurmi | **Phone Number:**(404) 895-0996 | **E-Mail**cynthia.nurmi@dot.gov |
| **Lead Agency Project ID:****FHWA** | **Other Project ID (i.e., contract #):** | **Project Start Date:**June 3, 2020 |
| **Original Project End Date:**December 2023 | **Current Project** End Date:December 2023 | **Number of Extensions:** |

Project schedule status:

X On schedule □ On revised schedule □ Ahead of schedule □ Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
|  **Total Project Budget** |  **Total Cost to Date for Project** |  **Percentage of Work**  **Completed to Date** |
| $640,895 | $0 | 0 |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
|  **Total Project Expenses**  **and Percentage This Quarter** |  **Total Amount of Funds**  **Expended This Quarter** |  **Total Percentage of**  **Time Used to Date** |
| $0 | $0 | 0 |

|  |
| --- |
| **Project Description**:Update of NOAA Atlas XIV for Montana and Idaho. Results will be published in Volume 12. |

|  |
| --- |
| **Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):**Continued to receive funding per commitments. |
| **Anticipated work next quarter**:Continue to receive funds for project. |

|  |
| --- |
| **Significant Results:****N/A** |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that** **might affect the completion of the project within the time, scope and fiscal constraints set forth in the** **agreement, along with recommended solutions to those problems).****None** |

|  |
| --- |
| **Potential Implementation:** N/A |