**HSM Implementation Pooled Fund Study**

**TPF-5(255)**

<https://www.pooledfund.org/Details/Study/484>

**Quarterly Report**

**July – September 2021**

**Participating Agencies:** CA, CT, ID, IL, KS, KY, LA, MI, MS, MO, NV, NJ, NC, OH, OK, OR, PA, TX, UT, WA, WV, and WI

**Total Funds Committed:** $1,555,000

**Total Funds Transferred to FHWA:** $1,478,664

**Total Funds Obligated:** $ 950,261

**Transferred Unobligated Funds:** $ 528,403

**Activities Accomplished During Reporting Period (July 1 – September 30, 2021):**

* Votes were tallied from member states on three project proposals and the initiation of a new pooled fund study
* Development of a statement of work for the three project proposals was initiated
* Updates on ongoing projects:
  + HSM Case Studies
    - The contractor (VHB) has been developing case studies. The following case studies were completed and posted to FHWA’s website during this reporting period: Wisconsin (intersection screening and project development) and Michigan (interchange alternatives analysis). Additional case studies featuring Texas, Alabama, Minnesota, Massachusetts, the District of Columbia, Florida are under development.
  + Development of Data Dictionary
    - A meeting to learn about a NHTSA-funded effort to link MIRE and MMUCC data, so the need for this data dictionary needs to be discussed.

**Activities Planned for Next Quarter (October 1 – December 31, 2021)**:

* Work will continue on developing HSM Case Studies highlighting projects in Texas, Alabama, Minnesota, Massachusetts, the District of Columbia, Florida , Vermont, Arizona, and others to be determined.
* The need for a Data Dictionary will be discussed with the representatives who submitted the original concept.
* A statement of work for the three proposed projects will be developed to prepare for a request for proposals
* FHWA will begin work to initiate a new HSM2 Implementation Pooled Fund Study