**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

Date: January 21, 2013

Lead Agency (FHWA or State DOT): \_\_\_Washington Department of Transportation\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |  |  |
| --- | --- | --- | --- |
| **Transportation Pooled Fund Program Project #**  *(i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX)*  TPF-5(114) Roadside Safety Research Program | | **Transportation Pooled Fund Program - Report Period:**  □Quarter 1 (January 1 – March 31)  □Quarter 2 (April 1 – June 30)  □Quarter 3 (July 1 – September 30)  XX□Quarter 4 (October 1 – December 31) | |
| **Project Title:**  Roadside Safety Research Program | | | |
| **Name of Project Manager(s):**  **Rhonda Brooks** | **Phone Number:**  **360-705-7945** | | **E-Mail**  brookrh@wsdot.wa.gov |
| **Lead Agency Project ID:**  **N/A** | **Other Project ID (i.e., contract #):** | | **Project Start Date:**  2005 |
| **Original Project End Date:** | **Current Project End Date: 2015** | | **Number of Extensions:** |

Project schedule status:

xx□ On schedule □ On revised schedule □ Ahead of schedule □ Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Budget** | **Total Cost to Date for Project** | **Percentage of Work**  **Completed to Date** |
| $2.1 million | $1.8 | 80% |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Expenses**  **and Percentage This Quarter** | **Total Amount of Funds**  **Expended This Quarter** | **Total Percentage of**  **Time Used to Date** |
|  |  |  |

|  |
| --- |
| **Project Description**:  The Roadside Safety Research program is designed to conduct research on roadside safety research. The priorities for research projects are defined by member states who serve on the Roadside Safety Committee. Texas Transportation  Institute is the research agency and has performed over 27 research inquires on various roadside safety features.  The Roadside Safety Committee invites other state DOT’s to join this collaborative research effort by making modest contributions to the pooled fund and participating in the development of the research inquiries. The Committee will meet again in the fall of 2013 in College Station Texas to review research results from TTI and to identify and prioritize new research inquires based upon the contributions made by participating states. New states interested in participating  should contact Rhonda Brooks at (360) 705-7945 |

|  |
| --- |
| **Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):**  Project progress can be viewed at <http://www.RoadsidePooledFund.org> |
| **Anticipated work next quarter**:  See Web Site <http://www.RoadsidePooledFund.org> |

|  |
| --- |
| **Significant Results:** |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that**  **might affect the completion of the project within the time, scope and fiscal constraints set forth in the**  **agreement, along with recommended solutions to those problems).**  **.** |

|  |
| --- |
| **Potential Implementation:**  Many research project inquires have resulted in modified design which have been accepted by FHWA. See the Roadside  Safety website for a complete listing of implementation activities. |