TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency (FHWA or State DOT):  __FHWA___________________________________________

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # (i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX) TPF-5(150) | Transportation Pooled Fund Program - Report Period: □ Quarter 1 (January 1 – March 31) (Quarter 2 (April 1 – June 30) □ Quarter 3 (July 1 – September 30) □ Quarter 4 (October 4 – December 31) |
| --- | --- |
| Project Title: Extending the Season for Concrete Construction and Repair, Phase III – Guidance for Optimizing Admixture Dosage Rate |
| Project Manager: Phone: E-mail: Fred Faridazar (202-493-3076) Fred.Faridazar@dot.gov |
| Project Investigator: Phone: E-mail: Lynette Barna (603-646-4503) Lynette.A.Barna@usace.army.mil |
| Lead Agency Project ID: | Other Project ID (i.e., contract #): IAA DTFH61-08-X-30031 | Project Start Date: IAA Effective Date Aug. 7, 2008 |
| Original Project End Date: Period of Performance 45 months from effective date ( 7 May 2012) | Current Project End Date: 01 JUNE 2013 | Number of Extensions: zero |

Project schedule status:

□ On schedule	□ On revised schedule		□ Ahead of schedule		□ Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Total Percentage of Work Completed |
| --- | --- | --- |
| $325,000 proposed project cost $325,000 received to date | $160,000 | 49% (based on project proposal) |

Quarterly Project Statistics:

| Total Project Expenses This Quarter | Total Amount of Funds Expended This Quarter | Percentage of Work Completed This Quarter |
| --- | --- | --- |
| $14,000 | $14,000 | 4% |

Project Description:

The purpose of the Phase III study is to develop tools and guidance to specify dosage levels of chemical admixtures used in antifreeze concrete to correspond with the varying weather conditions experienced at any job location. A user guide, including a series of design tables, will be developed describing admixture dosages to be adjusted for a specific level of protection. The guide will set dosage rates for general sets of conditions to provide a conservative level of concrete protection during the curing period. The dosage rates will account for the environmental conditions and concrete geometry. The guide will allow technicians to tailor mixture proportions and protective measures based on weather predictions for the first few days following concrete placement.

This quarterly progress report provides a summary of the effort expended and fulfills the reporting requirement in support of Interagency Agreement (IAA) DTFH61-08-X-30031, Modification 1 (signed 6 January 2009) between FHWA and the U.S. Army Engineer Research and Development Center, Cold Regions Research and Engineering Laboratory (ERDC-CRREL), entitled Extending the Season for Concrete Construction and Repair, Phase III – Guidance for Optimizing Admixture Dosage Rates.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):

1. Part 2: Developing design guidance. This effort continued this past quarter using the one-dimensional thermal model to evaluate a 6-inch concrete slab on grade exposed to freezing temperatures. This was the geometry used at the Ft. Wainwright, Alaska field demonstration. A total of five slabs were placed. The same base concrete mixture was used for each of the five slabs, only the admixture dosage rates were changed. Sensors were embedded in each slab to monitor the temperature during curing, as well as the ambient air temperatures. This data from the Ft. Wainwright, Alaska field demonstration was used as input in the CRREL one-dimensional thermal model to predict the concrete temperatures at the center of the slab as it cured. The predicted temperatures were compared to the measured temperatures.

Heat of hydration. The heat transfer characteristics are critical in modeling the thermal characteristics of concrete exposed to freezing temperatures. In particular, the heat generated by cement hydration must be understood. While heat of hydration curves have previously been produced, they reflect steady state conditions (ie. room temperature). An example is shown in Figure 1. Cement hydration is temperature dependent, under freezing conditions, such as antifreeze concrete has been exposed, heat of hydration curves were back-calculated using the measurements collected in the field. A heat of hydration curve was generated for each of the five Ft. Wainwright slabs. Comparison of the heat of hydration curves for each slab showed that based on the admixture dosages, the rate of heat generation was different for each slab. This result was expected given our level of familiarity with the concrete mixtures. This information is only the beginning of understanding the impacts of varying freezing temperatures on the rate of hydration and heat evolution.

Figure 1. Heat of hydration curve for cement under steady state conditions (based on Lea 1998).

Lea’s Chemistry of Cement and Concrete (1998) 4th edition, Peter C. Hewlett, editor, Arnold, London, W1P 9HE.

Initial design guidance. The one-dimensional thermal model may be used in developing the design guidance. This is under development using the temperature output from the thermal model, the freezing point of the antifreeze concrete mixture, and the strength gain (from compressive strength testing). Linking into the maturity characteristics, the method commonly used to estimate the in situ strength of concrete, provides the practitioner with a tool to evaluate and optimize varying admixture dosages. This analysis will continue during the next quarter.

2. Final project report. An outline has been developed and work has progressed on drafting the final project report.

Figure 2. Cumulative project expenditures updated for 3rd Quarter 2012 shown by quarter beginning January 2009 when initial funding for Part 1 was confirmed.

An estimated project timeline for Part 2 of the project is given in the table below. The vertical red dotted line indicates which task is currently under way. Application of the energy balance approach will continue during the 4th quarter of Fiscal Year 2011.

Table 1. Part 2 – Develop design guidance project tasks identified and estimated percent completion for Fiscal year 2011 4th Quarter. (Red dotted line indicates current quarter).

Anticipated work next quarter:

- Part 2 – Develop design guidance. This will continue during the next quarter to further explore the antifreeze concrete heat of hydration curves under freezing conditions. The thermal model will be used to evaluate different scenarios useful for developing the design guidance;

- Thermal model. The thermal model computer code will be adjusted for user data entry;

- Contract. The contract with the subcontractor (Charles Korhonen) expired in May 2012. A new contract is being pursued to continue assessing the datasets used in developing the design guidance;

- Draft final report. Preparation of the final report will continue.

Significant Results:

A mathematical model, based on heat transfer principles, has been developed describing the interaction of a 6-in thick concrete slab placed on grade. Currently, the model neglects the effects of solar radiation and evaporation, and does not include insulation. For the case of the slab on grade, the material layers and thicknesses are defined, including the substrate. Daily maximum and minimum air temperatures, and the time of occurrence were used as input parameters. Measured air temperatures may be used as input, or maximum and minimum predicted daily temperatures may be used. With the daily maximum and minimum temperatures, hourly temperatures are generated using a sinusoidal function.

The heat of hydration of the cement in the mixture is input to determine the amount of heat generated as the concrete cures. The estimated internal concrete temperatures as the concrete cures are output on an hourly basis in tabular form. During this quarter, heat of hydration curves were generated from our dataset and then used in the one-dimensional thermal concrete model. The heat of hydration curve for each slab were different, showing the effects of varying the admixture dosage.

The thermal modeling tool enables predicting internal concrete temperatures as it cures to compare with measured temperatures collected from field cured antifreeze concrete. The output showed good agreement with the measured concrete temperatures. The model will be a valuable tool to evaluate differing admixture dosages for antifreeze concrete formulations. This is a significant step in further building our understanding to predict the strength gain of antifreeze concrete subjected to freezing or sub-freezing temperatures.

The report for Part 1 of the project is available at: http://www.crrel.usace.army.mil/innovations/cold_weather_concreting/antifreeze_admixtures/extending_the_season.html

Circumstance affecting project or budget (Describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope, and fiscal constraints set forth in the agreement, along with recommended solutions to those problems).

Nothing to report at this time.

# Footnotes

Effective 21 December 2011, project end date changed as per scope of work approved 7 August 2008.

Phase III Extending the Season for Concrete Construction and Repair, Guidance for Optimizing Admixture Dosage Rates, Project Proposal, USAERDC-CRREL, submitted 2004.