**HSM Implementation Pooled Fund Study**

**TPF-5(255)**

**Quarterly Report**

**July – September 2017**

**Participating Agencies:** CA, ID, IL, LA, NC, KS, OH, OK, OR, MI, MS, NJ, PA, MO, NV, UT, WA, WV, and WI

**Total Funds Committed:** $1,455,000

**Total Funds Transferred to FHWA:** $1,233,078

**Total Funds Obligated:** $ 809,448

**Transferred Unobligated Funds:** $ 423,630

**Activities Accomplished During Reporting Period (July 1 – September 30, 2017):**

* TPF-5(255) State representatives met virtually on September 5. At this meeting, participants received a software demonstration on one project, and kick-off discussions were held on two others. There were also updates on other ongoing projects, as well as general updates from each participating state.
* “Safety Performance for Intersection Control Evaluation” Project:
	+ The contractor demonstrated the 1st draft of the SPICE tool spreadsheet on September 5, 2017.
	+ Tool was disseminated on September 21, 2017 and comments were request by September 25, 2017.
* “Network Screening Noteworthy Practices”
	+ Kick-off discussion was held September 5, 2017.
* “Safety Analysis Needs Assessment for PBPD and TSMO” project:
	+ Kick-off discussion held on September 5, 2017.
* “Highway Safety Benefit Cost Analysis Tool” Project:
	+ 2nd draft was disseminated to FHWA August 21, 2017. Additional revisions were suggested by FHWA
	+ Tool will be demonstrated to the State representatives on October 3, 2017.

**Activities Planned for Next Quarter (October 1 – December 31, 2017)**:

* Hold working sessions with TPF-5(255) State representatives to update them on funded projects
* Hold virtual quarterly business meeting of State representatives.
* “Highway Safety Benefit-Cost Analysis Tool” Project:
	+ 1st draft of Tool will be disseminated for State representatives
* “Safety Performance for Intersection Control Evaluation” Project:
	+ The contractor will be developing a 2nd draft of SPICE tool based on feedback received.
* “Network Screening Noteworthy Practices” Project:
	+ Contractor will be developing the 1st draft of the report
* “Safety Analysis Needs Assessment for Performance-Based Practical Design and Transportation System Management and Operations” Project:
	+ Contractor will develop 1st draft of the report and will provide an overview via a 2nd virtual meeting with the State representatives.